## Sheet1
Weekly Report
|  | Team Name | SM Team
|  | Period | 2014/09/08 ~ 2014/09/12
|  | Member | Phon Visoth
|  | Reporter | Say Seakleng
Overall Status
No. | Product/Customer | Started | Planned | Description |  |  | Progress Status(%) | Finished
1 | Create Plugin bizMOB 3.0 | 2014-08-11 | 2014-09-05 |  |  |  | 100 | 2014-08-09
Issue Details
No. | Product/Customer | Issue on | Issue off | Description |  | Requirement for solve the issue |  | Remark
1 | Create Plugin for bizMOB3.0 | 2014-11-13 |  | AppGallery and ImageView
This Week
No. | Product/Customer | Task Div. | Started | Task Title (Redmine Task, Title(Back Log), Task Number) |  | Details Description |  | Charge | Status(%) | Finished
1 | Research With Real Time FrameWork |  | 2015-01-05 |  |  |  |  | Visoth | 100
2 | PushBots |  | 2015-01-14 |  |  | Resgister push iOS APNS |  | Visoth | 100
3 | Research on Thread and CoreData |  | 2015-01-12 |  |  | Safe thread and unsafe thread
Next Week
No. | Product/Customer | Task Div. | Started | Task Title (Redmine Task, Title(Back Log), Task Number) |  | Details Description |  | Charge | Target(%) | Remarks
1 | Research on Push Notiifcation |  | 2015-01-16 |  |  |  |  | Visoth | 100
Schecdule for Dayoffs
No. | Name | Days | From | Return | Reason